## Meeting Minutes September 2022
Meeting Type | Sync-up | Voicebot MVP Discussion | Status Meeting | Sync-up | Status Meeting | VA.gov Content Team Meeting | UDO Meeting | Status Meeting | Sync-up | Status Meeting
Date | 2022-09-26 | 2022-09-22 | 2022-09-22 | 2022-09-19 | 2022-09-15 | 2022-09-13 | 2022-09-09 | 2022-09-08 | 2022-09-06 | 2022-09-01
Notes | •Follow up with RY about first set of users for internal usability testing (ie. what does she need fmro us to start recruiting people?). Most likely will want to see XD prototype. •BAH team to provide a pulse check at next status meeting for user testing and readiness for VBA. | Regina: - No issues with bot starting after Spanish - No existing authentication at NCC level, but would like it to potentially pass authentication straight to agents - They will send information on what agents use to authenticate - Third party authorization form, the bot will not be able to consume this. - Huge question on authentication, or how to authenticate - Access to FAQ documents - compile based on flow needs - Regina to connect Process team to create content right off the bat (Michelle) - Regina is fine giving us VA testers including agents on their end Plan as suggested by Luciana:- Wrap up EVSS+Integration with Brian Mahlum and new flows by mid-October - Flesh out internal usability testing w/XD - Start internal testing (one week) - Meet with VBA and IVR team (November) on findings. | •KB and LM interested in seeing more of a UX prototype demo. •Make sure we're not going over our credits for Google. •Begin looking more into Google training. At BAH site, find out about possible travel under PTEMS for non-local team members. | Q: Vet testing before or after dev? A: Before. We want Vets to listen and provide feedback (no text review). If XD works for that, we can do that. Meeting with Vets is important because voice hasn't been done before and we want their input right away. And make a continuous testing iteration. -LM | •KB and LM to look at workflows and provide feedback on Mural. •Schedule a follow up call with the content team. •Set up a regular meeting cadence with Brian Mahlum, aiming for every other week or so. | •Voicebot team and content team to set up a series of meetings to begin developing a high level content strategy. Aiming to start end of September to establish a cadence of meetings in October. •BAH team to send a summaries of NLU content design researh before content meetings •VA.gov can provide content briefs | Agents can... •Update phone #.s, addresses, etc.; can add dependents •Share payment info for a positive decision •Send emails with links to forms and other info; could send an email to one that is not registered with the account. (This is not an automated process) •See when a decision was made (often the letter is sent on the same day.) •Make a diary note for intent to file. Agents cannot/don't... •Provide adjudication •Share payment amount for a negative decision. Systems: •VBMS •Caseflow, which is related to appeals (only a certain subsection of agents can do this). •Bot is not in the business of interpreting contexts and rationalizing, which is a capability of an agent. •Potential areas of interest for the Voicebot team to look into: -Drafting language for negative decision -Engaging with letters sent (ex: I see there's been a letter mailed to you. Have you received it?) | •Glenn put in a ticket and will follow up on eGain data. •Utterances for VCL: Luciana to reuest download for that list. •Pushing for Dialog CX but it might not be the one we end up using. •Kate asks to go through AWS link--could be opportunities to use free trials. Play around with this and get back to Kate •Gian to look into giving Luciana, Kate and Clive access to sandbox environment. •The biggest blocker to the launch date is the license fiasco. ATO won't hinder launch date. •For prototyping, make sure we are testing in a voice environment, not just text. •For now stick to claim status and PACT--direct deposit and benefit letters can be fast follows. | Q: With the launch date of Feb 1. 2023, what does this entail? Production or dev? A: This date is for production with a percentage of Vets. -LM •We are pursuing Dialogflow CX. •Gian to schedule a call for this week to go over tentative project timeline. •LM suggests creating error flows to document scenarios or capabilities the bot cannot handle. •Unified Service Desk--Kate will ask Chad for more detail. Part of the CRM (VBMS?). •Kate to schedule a meeting with Chad Estep about potential UDO demo. | •Sync-up scheduled for 9/6/2022. •We've got AVA data--containers in Azure data lake. •CRM/UDO data=VBA data. Already in CXDW. Ahmend to connect with Chad as possible SME to help with data analysis. •BAH team to decide on a date to present findings with the VA; aiming for week of the 19th. Presentation to include a research consensus, draft flows, potential MVP and identified information gaps. We need VBA help with creative construction of custom content. •Meeting with Content team and Brian Mallum's team week of the 12th. •Unified Service Desk--Kate will ask Chad for more detail. Part of the CRM (VBMS?). •LM recommends beginning usability testing first or second week of October. •First outreach has been sent to Dr. April Foreman (VCL), but she needs permission to engage with the Voicebot team first.
Action Items |  |  | •Ty or Julie to schedule UX prototype demo for next week with LM and KB. |  | •Gian to schedule follow up with Brian Mahlum. •Grace to schedule follow up with the content team. |  |  | •BAH team to explore AWS free trials and get back to Kate. •Gian to look into giving Luciana, Kate and Clive access to sandbox environment. | •Gian to schedule a call for this week to go over tentative project timeline. | •BAH team to begin preparing for VBA meeting.
Notetaker (name) | Grace Goodenough | Luciana Morais, Grace Goodenough | Grace Goodenough | Grace Goodenough | Grace Goodenough | Grace Goodenough | Grace Goodenough | Grace Goodenough | Grace Goodenough | Grace Goodenough

## Meeting Minutes August 2022
Meeting Type | Sync-up | Status Meeting | Sync-up | Status Meeting | Status Meeting | Sync with Chatbot | Design, Research and Content Sync | Sync-up | Status Meeting | Demo (Microsoft Conversational AI) | Sync-up | Status Meeting | Sync-up
Date | 2022-08-29 | 2022-08-25 | 2022-08-22 | 2022-08-19 | 2022-08-18 | 2022-08-15 | 2022-08-15 | 2022-08-15 | 2022-08-11 | 2022-08-09 | 2022-08-08 | 2022-08-04 | 2022-08-01
Notes | •LM provided feedback on workflows. •Egain data is health chat data. Dennis Roach to give 1 year's worth of data, which might have components around claims. •It's fine to look at alternatives later, but LM recommends to ocus on the biggest bucket of general status claims now. We don't want to inflate the scope too much. •LM can pull chatbot claim status data transcripts. •BAH team can show the flows we have to Lighthouse API team to let them know what we're trying to get to. See if these changes will be included in the updated API? •We need to speak with VBA about proper tagging and they might have ideas for API updates. But also think beyond API, may need manual content that VBA helps with. •Feb. 1, 2023: notional date for launch. Then do a fast follow with updated APIs and manual content. All about iteration. •Aiming for week of Sept. 19 for meeting with VBA. We can show them what we have done so far and what we need help with. •Three main Q's: -Why is it taking so long? -What does the status mean? -I see you need more documentation for me, how do I send it? | •CRM data is already in CXDW -Access for BAH team still pending -It's the raw data (not structured), we have to make sense of it. -Chad may be able to help with the tables portion and connect some of the dots. Let Kate know when we get to that point and she will connect us with Chad. •Aim for first or second week of September for research presentation. •Luciana to review workflow and provide feedback as soon as she can. •Luciana will let us know when the content team is ready to meet with us and talk about PACT Act. •Cisco telephony, transcripts, VHA CommunityCare POCs: all on Brian Mallum's team. Luciana to connect with Brian to see what his bandwith is like for the rest of August. •AVA data is ready to share, but unsure where to upload it. Luciana looking to make a Sharepoint. •BAH team shared a summary of VA.gov search term analysis. •Luciana to schedule a meeting with Dr. April Foreman (VCL) for next week or week after. •Discussions are in place about who's going to procure the Dialogflow license. Fedramp level is not a concern. •VA environment to support Voiceflow--may not happen. It's a topic to surface with Sophie. Luciana tried to request an increase in Fedramp for Voiceflow and it was denied. •Luciana requesting final assessment/concrete analysis of the team allocation we want. | •Workflow feedback from Kate: -What we really need to focus on is: Is the current level of info provided to the veteran sufficient? -Are we all looking outside of claim status for potential MVPs? Because the claims status is pretty complex, are there other options for MVPs to present to the business? (ex: dependency verification) -Is there a way to verify mailing address for decision letters? -The visual makes a lot of sense and is easy to understand. •Once we're ready, get into contact with Brian Mallum’s team to reuse their authentication system •Kate doesn’t think CXDW will give us how vets ask for things, caller intents, etc. Will look into getting access to call recordings from Calabrio. •Expectations for an upcoming presentation: how are we preparing for engaging the business? what are other self service options for MVPs? | •Proposed updates to APIs need to be backed by data and context -Ex: VBA submitted an innovation request to increase the tracking tags in order to address details/nuance in claims. This could provide context for the Lighthouse API team. •Re: authentication. We have to meet with the identity team. The bot will sit on Brian Mallon’s existing telephony structure, so we might pass that authentication system over to the voicebot. Early September-meet with Brian. •Ahmed to connect Luciana and team with VHA CommunityCare team to see how another group is tackling claims (potential POC: Sharon Smith). •Luciana to schedule calls with: Brian Mallon's telephony team; Dr. Foreman and the VCL team; content team. •Crisis VCL workshop mural provided; major issues might translate to the bot. https://app.mural.co/t/departmentofveteransaffairs9999/m/departmentofveteransaffairs9999/1628528882317/864da552217c851356b523e4b8af9c062188d025?sender=u52cdc9cfa21df7cc61484771 •Bot is not supporting the VCL, just something in the background. Bot will understand the intent of a crisis and transfer to the VCL. •Hold off on building an environment for voiceflow prototype. •45 minutes for status meetings going forward. •BAH team to begin brainstorming a presentation of all the data we’ve been combing through and learnings we’ve found to show Luciana and team. | •Kate to have a call with CXDW today to see who is the best to connect with for data requests •Kate to schedule a meeting for Amber, Millie, Gian and Luciana to make sense of Cisco data •Cisco is telephony data. Separate from CRM data. •Luciana to set up a meeting with the content team to get an overview of PACT and how to communicate PACT. BAH team start familiarizing ourself with PACT Act content. •BAH team to assess if a September work kickoff still works and if we will have enough research to start meeting with VBA and Brian Mallon's team. -Work kickoff meaning: at the very least, meeting with VBA and narrowing down the scope for development starting in October. | •Collaboration cycle: team that makes sure there is consistency across products; part of the office of the CTO. Info about cycle orientation to be sent out. POCs •Beth Potts and Danielle Thierry - content specific issues •Dr April Foreman - VCL SME •No voicebot style guide and content guides yet; something to tackle in the near future once MVP is decided •Speaking with veteran crisis line folks is a requirement before launch. •Topics of considerations for AI: disability/accessibility, equity, language | Insightful learnings from research findings on the VA mobile app's pharmacy feature: •Participants wanted more of a confirmation when submitting refill requests •Participants wanted a place to view all of the “in process prescriptions”. •Participants have a lot of faith in VA prescription shipping. They’ll typically only look at tracking if something gets lost or to verify if it’s been shipped. •Participants expressed confused around status meanings •Participants reported MHV reported login as a pain point for them (“3 billion ways to log in”) | •We don't want to necessarily translate the chatbot functionalities to voicebot. While they're both conversational experiences, people ask for different things when they text vs. call. Some things that work with the voicebot might not work for the chatbot and vice versa. •Shane Strassberg will be the POC for all VA research and can help our team figure out all the research that has been done. •Design/research/content meetings at 1pm on Mondays. •Paperwork in progress for platform decision of Google Dialogflow. *not official* •Luciana to look into getting data for search terms on VA.gov •Begin thinking about consolidating and uploading our research to GitHub | •All status meeting decks and meeting minutes to be uploaded to VA Sharepoint •John Rocco's team is working on NCC claims call metrics •Gian, Millie and Ray approved for DataBricks access •Claims API is not sufficient enough in understanding nuance of veteran requests •Claims sync with the Office of the CTO next week to see if there is any existing user interviews with the claim status tool •Kate has a data request document and will send to BAH team to see if we want to add anything before sending to the NCC team •Luciana to check in with Chante on NLU platform decision •Team is signed up with Slack | •Microsoft's NLU strategy: ⁃Intelligence based -Natural communication: what can you do?; I need assistance; please help. -Evolving -Complex Interactions -Less interactions needed -Intent: -What does the user mean?: I want to talk to an agent; connect me to a human please -Entities (the important pieces of the utterance): -User provided information -Primitive types: numeric (zip code, phone number), labeled data (city, state) -Complex types: user defined (pizza toppings) •Answering a topic, going off topic and then getting back? Feature not available yet. •SaaS platforms can handle spikes in volumes. Expected workloads for govt agencies •Demo Scenario 1: Understanding user intent, homelessness •Demo Scenario 2: Locate the nearest medical center | •Data from Chante: ⁃They are Tier 1 record types -Won't tell you what they asked for and how they asked for it •Kate and Luciana had a meeting with Regina's team (NCC) last week •Kate and John Rocco looking into what NCC data exists in the CXDW. •Millie started discussions with Karan and Justin about the APIs related to claims, but no response. Kate thinks the chatbot team would be knowledgeable about this. | •Luciana to push for VoiceBot for team name ⁃Plan B: AI Agent, AI Assistant, Conversational IVR •Kate and Luciana meeting with NCC today 8/4, hopefully get some times to schedule a formal kickoff •Luciana to ask Chante, Trish and Sophie for status of platform decision •March 2023 (Q2): Launch MVP Pilot. Scope of pilot is TBD •Reach out to karan.krishnani@va.gov and justin.trieu@thoughtworks.com for VBA user testing data | •Voiceflow demo ⁃Sufficient enough to show the OCTO team to get them to understand what we're trying to do -Remove any mentions of VA on Voiceflow -If its not working well, how will we test this with veterans? Just something to think about. Might have to do a wizard of Oz to test responses but this isn't ideal. -Another solution to Voiceflow flaws is to get a free lambda acc to create a lexflow -Voiceflow is to gauge the quality of responses. Don’t worry so much about linear vs non linear NLU •Chante uploading call center data to Teams (GFE access) •Luciana found some people who are working with claims and is setting up a meeting next week to start understanding the process and what we want to achieve with claims. •Luciana and Kate having a touchpoint with VBA to get them started on working with us •OCTO demo meeting next week.
Action Items |  | •BAH team to review crisis mapping mural and deveop questions/ideas for conversation with Dr. April Foreman (VCL). |  | •Sunayna or Julie to send workflows to Luciana and Kate. | •BAH team review website content on PACT Act. •BAH to assess and give a pulse check next week to Luciana and team. |  |  | •Begin creating workflows to paint a picture of what is available currently and what we are missing. |  |  | •Gian to upload status meeting decks to Voicebot Teams site (VA side) | •Julie to send MURAL roadmap to Luciana and Kate •Millie to reach out to Karan and Justin for VBA claims data | •Brainstorm new team names •Show roadmap at Thursday's status meeting
Notetaker (name) | Grace Goodenough | Grace Goodenough | Grace Goodenough | Grace Goodenough | Grace Goodenough | Grace Goodenough | Grace Goodenough | Grace Goodenough | Grace Goodenough | Grace Goodenough | Grace Goodenough | Grace Goodenough | Grace Goodenough

## Meeting Minutes July 2022
Meeting Type | Sync-up | Status Meeting | Status Meeting | Sync-up | Demo for MyVA411 CUI Google | Status Meeting | Chatbot discussion | John Rocco Q&A | Sync-up
Date | 2022-08-01 | 2022-07-28 | 2022-07-21 | 2022-07-18 | 2022-07-15 | 2022-07-14 | 2022-07-13 | 2022-07-11 | 2022-07-07
Notes | •Voiceflow demo ⁃Sufficient enough to show the OCTO team to get them to understand what we're trying to do -Remove any mentions of VA on Voiceflow -If its not working well, how will we test this with veterans? Just something to think about. Might have to do a wizard of Oz to test responses but this isn't ideal. -Another solution to Voiceflow flaws is to get a free lambda acc to create a lexflow -Voiceflow is to gauge the quality of responses. Don’t worry so much about linear vs non linear NLU •Chante uploading call center data to Teams (GFE access) •Luciana found some people who are working with claims and is setting up a meeting next week to start understanding the process and what we want to achieve with claims. •Luciana and Kate having a touchpoint with VBA to get them started on working with us •OCTO demo meeting next week. | •Meeting with Vlad is cancelled; go through Brian Mallon first. ⁃Mallon's team wants to give us an overview of the existing architecture of the current call center system (aiming for mid-August). •Chante's data to be put in Teams due to possibility of PII (GFE access) •Chante took the action item to set up a touchpoint meeting with Sophie for get the NLU platform decision. •Waiting to schedule VBA/NCC kickoff until they hear back from Regina Young. •Luciana will speak with Chante on what groups to speak to/collaborate with for claims. •Luciana started convos with the CXDW team about setting up where to store voice data/build a data lake within the govt system. | •Kickoff with all stakeholders: VA will take the lead on organizing. ⁃Luciana to meet with internal stakeholders (ex: Brian M) first before kickoff ⁃Kate developing a deck -Target date: first week of August •Luciana to connect with Chante about transcript data and other call center data (will need GFEs to access) •Luciana to step back from platform decision due to a conflict of interest. Kate, Chante or Sophie and Trish’s team will take the lead on this. All discussions about licenses should switch to those people. •Maximus IVA performed a demo for the VA (they are FedRamp moderate) •Kate to share skillset information for dev hiring from Google | •It is not on the BAH end to make the platform decision. The best BAH can do is give a recommendation. Ultimately, the decision is Sophie and Trish’s team at the VA level. Google and Amazon are comparable in terms of NLU, but the devil is in the details with the Fedramp and integration with call centers. •Luciana suggests to do a comparison test between the current decision tree and NLU. -Access to veterans is a process of recruitment. Whenever you have a test plan and research plan approved by Kate and Luciana and met with Shane Strassberg, we can start with recruitment which can only take three days to get the participants. | •Scenario 1: Homeless Veteran •Scenario 2: English to Spanish •Scenario 3: Comprehensive use-case: finding a medical center, scheduling a vaccine appointment, checking claim status, getting authenticated, along with sentiment analysis occurring and ending the conversation by being transferred to an IVR. -Authentication -Integration with Google Maps and Geocoding API (finding a VA medical center) -Integration with SMS text capabilities -Interrupting the flow and asking a question -Responding to FAQs -Integration with Appointment Management system (scheduling an appointment) -Checking claim status -Sentiment analysis -Skills based routing *Demo recording uploaded to Teams folder (GFE access) | •We need to aim for FedRamp high, because if we’re doing self-service or any type of authentication with PII, we will need high. Luciana to sync us with someone to explain FedRamp process. We need to figure out how to take Dialogflow from moderate to high. The most important factor to consider is how these platforms work with existing call centers. •VoiceFlow is okay for prototyping. You should only use the free version and should be connecting any APIs to it. The flows need to be high level, and the dialogues need to be written as carefully as possible. The flows should only be made to have the veteran interact with it and give some opinions. Make sure Veteran data is not being stored on VoiceFlow. •For chat, Microsoft PVA’s function works but it’s not quite there yet in the voice environment. PVA is not a good product nor does it provide a good experience. If Dialogflow works, we might want to switch the chatbot to that. | Chatbot project overview •Most veterans don’t go to va.gov as a source of truth, even though there are no competitors. Veterans utilize other systems of support, such as in-person community groups or online Reddit threads. •Call centers face immense pressure due to call volumes and call content, which is often complex, stressful and emotionally charged. •The chatbot serves as an in between for va.gov and call centers by providing guided self-service. •Launched as an AMA bot focusing on the following content topics: COVID-19, benefits, contact centers, claims (mostly compensation claims) and appeals. -Developed through user research, call center data, live transcript analysis and actual user interactions. •Engage Vets for user studies by working with Perigean on user profiles and scheduling. -Certain groups of people will be missed, such as homeless populations, but the goal is to offer all remote studies for wide engagement. •Decided on Microsoft PVA because most call centers use Microsoft, which might aid in chatbot connection to live agent further down the line. | Education data spreadsheets •This report is showing all the different call types that are set up for VBA for all the various contact centers that are in VBA. These are all the different call queues that agents can be put it into to answer questions. -Offered: how many calls came into that call type. -ABAN: caller hung up -Flow Out: the caller actually went to an agent. -Other: they hung up in the process or the call got disconnected. -Short Call: the caller was on their way to an agent and call got severed on either end. (Ex: caller was waiting on hold, but then found the information and then hung up or caller was driving and hitting a dead spot). -Return: Rocco will look into more. -Other + ABAN + Flow Out = Offered. NCC All Calls spreadsheets •Showing all possible call types for NCC across multiple sites, and all call types within VBA NCC IVR flow. •Some call flows are detailed, but most don’t have the specific call types. Looking at the flow of the IVR rather than the flow of the call routing. Don’t marry the workflows with the spreadsheets. | VBA IVR work flow: •This is the latest version. The announcements for VBA are going to change ongoing, so the direct deposit isn’t there by the self-service is still there. We will share documents of the lower level of the process flow by next week. Reach out to John Rocco for questions. •1-800-827-100 is the main NCC line and 1-866-258-0341 was the old appeals number, assuming it reroutes to the main NCC line. •The overall goal is for NLU to replace the existing decision tree the call center system has. To get there, we are breaking these down into pieces we can handle and doing small releases, with the first one being VBA. VBA is the call center with the most need for revamping, and they are willing to work with us throughout the process. We want to help the veteran and generate less calls for the VBA. This is not necessarily the work flow we will use, as there is additional discovery to do with the VBA. •One of the biggest buckets of calls is claims status. The Chatbot team is looking at how to improve claim status and the Voice team should look at this as well. The biggest problem with claims status is that we don’t have the background info that defines those decisions. When veterans get their claims status, they’ll often say they already have the given information, but want to know why it’s taking so long, what does this document mean, etc. They’re rationale issues that a bot or Voice will fail on. That’s a foundational problem at the VBA level. VBA call center agents also use the claims status tool so they can’t give any more information than the bot or Voice.
Action Items | •Brainstorm new team names •Show roadmap at Thursday's status meeting | •Focus research efforts on disability compensation claims. •Luciana wants a glimpse at what we’ve built with Voiceflow. Show a demo at next week's sync up. | •Take a look into claims so can we build a claims voice self service. This could serve as a potential mock for a best use case of ideal state to test with vets. -A potential discovery strategy: ideal state of claims -Attempt to answer questions of nuance and transparency on the process of claims decisions -Work with the chatbot team to share and collaborate on research | •In discussions with Google, consider asking what skillsets we need to do a good job with this. Kate might be getting this information as well and will forward along. |  | •Take some time to look at Lex. •Explore user interviews around voice and focus on friction points that Veterans are having with the phone systems. •Put together a simple IVR that doesn’t need to have an interaction, but a task scenario for participants (ex: checking claims status through existing decision trees vs NLU) and get a perception test of which Veterans like better. | •Engage with Chante Lantos-Swett for call center data and understanding their pain points |  | •Speak with John Rocco about workflow (meeting arranged by Kate) and include him in check-ins in the future. •Meet the VBA call center team (Regina Young and her team).
Notetaker (name) | Grace Goodenough | Grace Goodenough | Grace Goodenough | Grace Goodenough | Grace Goodenough | Grace Goodenough | Grace Goodenough | Grace Goodenough | Grace Goodenough

## Meeting Minutes June 2022
Meeting Type | Initial Scope Meeting
Date | 2022-06-29
Notes | •First priority: Chatbot for MyVA411 for VBA -Research, select, develop, deploy ChatBot app for MyVA411 (VBA). -Agents at the VBA are swamped with phone calls, they are hoping a ChatBot can triage and provide self-service -ChatBot should be able to reduce and deflect calls -Two ChatBot platforms are Google Diaglogflow and Amazon Lex (Kate Buker to share her research/docs) -Documentation and decision tree for MyVA411 for VBA is available. -By the end of the project we need to have built a proof of concept. Needs to have been tested and run adjacent to the existing MyVA411 system. -We will need to identify and establish test environments •Second priority- replace AudioCARE -AudioCARE is being replaced due to contract issues, contract ends Sept 2023 -Luciana would like the platform we select for MyVA411 to be the same as AudioCARE -AudioCARE business rules / logic could be fine, but we may need to make it better
Action Items
Notetaker (name) | Gian Bustillo

## Outstanding Questions
Question
For who?
Topic
Answer?