## Slide 1
Voicebot
Booz Allen Status Meeting
March 2, 2023

## Slide 2: Agenda
ML Workstream
UX Workstream
Technology Workstream
Integration Workstream
Ad Hoc Items
Open Forum

## Slide 3: ML Workstream
Item | Description | Status | Next Steps | Owner
PACT Act use case | Voicebot will use training phrases extracted from Chatbot transcripts to develop intents for classification of PACT Act-related user inquiries. | Completed ticket VOICEBOT-304 for the PACT Act training received by Kate on 2/9 VOICEBOT-305 created to identify PACT Act intents which need additional training phrases Completed ticket VOICEBOT-258 to Group responses from PACT Act Survey Received claim training phrases from Shiva in January | Review and import training phrases into Voicebot VA to decide on proposed intents provided by Booz Allen on 2/14 Receives Training phrases around Toxic Exposure from Shiva. Booz Allen and VA to review and finalize intent list | Booz Allen
Claim status use case | Voicebot will use training phrases extracted from AVA submissions and Chatbot transcripts | Received claim training phrases from Shiva in January Removed PII from claims training phrases | Team to review training phrases and assign to claim status intents | Booz Allen
Notes: As user inquiries evolve, supplement training phrases: newer data, test subjects, etc
eGain data to be made available
Exploring availability of AVA data in CxDW
Step 1. train a small number of intents in dialogflow with quality training phrases. If we can achieve high classification accuracy on those intents, namely low false positives and low false negatives, that would be a and if we and let bot perform well at classifying those, with everything else
End-user input (speech) > intent classification (success determined by quality of training phrases) > bot response with relevant and approved content > end-user input >> classification of bot response
(claim status and PACT Act alone can easily grow into 10-20+ distinct intents if we pursue self-help options deeply or they could just be two intents and there are now flows, just classification and routing immediately back to cisco).
UX – content, procedures, approvals, best practices, user testing, flow design and re-design
ML – two-fold application: 1) process large datasets to generate run language models on data VA has collected that captures users’ interactions with the contact center to extract examples of end-user inquires from existing data that most closely resembles what voicebot will encouter, ensure variety utteranceslanguage models

## Slide 4: UX Workstream
Item | Description | Status | Next Steps | Owner
Content creation for Voicebot responses: re: claims | Develop content, procedures, and get approvals; documenting how Voicebot will support claims questions. | Team is collaborating with Danielle and Megan on claims content strategy. Megan finalized claim status definitions on 2/10. | Transfer all claim statuses with their corresponding definitions to Dialogflow. Team to work on Version 3 of claim status flow in Visio after prototype for Test session B is ready to document any changes. | Grace/ Sunayna
Content creation for Voicebot responses: PACT Act | Learn about PACT Act and develop content responses. | Team is scraping Reddit for Veteran questions and sentiments. | Form content around scraped questions. Megan to review existing PACT Act content by 3/24. Team to work on V3 of PACT Act flows after prototype for Test session B is ready. | Grace/ Sunayna
Content for introduction messaging, errors, parameter prompts, etc. | Develop content for managing user expectations throughout conversation | Team is diagramming error flows in Visio and documenting responses to identified error categories. Introductory/welcome content finalized by Megan on 1/27. Authentication prompts finalized on 2/24. | Megan to review conversational phrases by 3/10 and error messages by 4/7. | Grace/ Sunayna/ Nicole
User Research | Efforts to elicit design inputs from end user research and testing | Completed caretaker flow on 2/17 for team reviewed Tickets created for work needed for flows | Team working on tickets for supporting flows for Session B | Nina

## Slide 5: Technology Workstream
Item | Description | Status | Next Steps | Owner
Google DialogFlow | Implementing Voicebot solution in DialogFlow | Consuming new PACT utterance data analysis and inputting newly identified training phrases into Dialogflow Building application which will assist in maintaining training phrases in a single place for dev consumption and efficient inputting into DF | Implement QA regression test period once all requirements are met for User test session B. | Josh / Nicole

## Slide 6: Integration Workstream
Item | Description | Status | Next Steps | Owner
VA Sandbox | A sandbox Voicebot development | VA working on creating sandbox | Once sandbox is set-up, Booz Allen will set-up Voicebot and begin exploring integration into VA services | VA
Cloud Webhook Service | Cloud Function being used for webhooks in DialogFlow | Adding new mock data for test users in BAH Google cloud function ECSO Intake meeting held on 3/1 | Booz Allen to complete requested information in CloudKey ECSO to re-send MOU's to VA for signature | Booz Allen

## Slide 7: Ad Hoc Items
Item​ | Description​ | Status​ | Next Steps​ | Owner​
ATO acquisition | DTC preparing for ATO | Booz Allen provided response to questions in PTA on 1/17 Met with DTC on 1/30 to review PTA Booz Allen updated Data Elements spreadsheet on 2/28 | ATO approval estimated to take 6-10 months Security Assessment call scheduled for 3/8 | Booz Allen / VA
Meeting with Regina | Voicebot to meet with Regina and team to share User Session A insights | Meeting Regina and team occurred on 2/15 at 9am | Follow-up email was sent to Regina on 2/15 and 3/1 inquiring for scheduling meetings with SME's and decision makers. | Booz Allen
Project Documentation | Ensuring all project documentation is accessible | Booz Allen working on Project Summary deck | Project Summary deck is being reviewed internally New resource to be used to continue to iterate on deck | Booz Allen

## Slide 8: Open Forum
Questions / Open Discussion

## Slide 9: Appendix

## Slide 10: Project Overview
Detailed scope for Omnichannel project will be voice.
Discovery through building and learning—build it, learn from it, iterate it.
  With an overall strategy of transitioning MyVA411, transition VBA to using a Natural Language Understanding (NLU) platform.
    Determine the problem categories and point of transition.
  Through learning and understanding how self-service and triage can be supported through voice channels, assess another product which may replace AudioCARE.
  Stipulations:
    Projects must have a customer experience and Omnichannel mindset toward best customer experience for Veterans.
    Small iterative releases, solutions to run in parallel with existing solutions to Veterans are not negatively affected by our transitions.
    All products must have Veteran input.