## Slide 1
Voicebot
Booz Allen Status Meeting
March 23, 2023

## Slide 2: Agenda
ML Workstream
UX Workstream
Technology Workstream
Integration Workstream
Ad Hoc Items
Open Forum

## Slide 3: ML Workstream
Item | Description | Status | Next Steps | Owner
PACT Act use case | Voicebot will use training phrases extracted from Chatbot transcripts to develop intents for classification of PACT Act-related user inquiries. | Completed intent matching for the PACT Act training phrases received from Kate. Completed grouping responses from PACT Act Survey. Completed intent matching for the PACT Act training phrases received from Chatbot transcript analysis for Nov-Dec'22 and Jan-Feb'23. | Booz Allen to review existing training phrases and finalize list. Booz Allen and VA to review and finalize intent list | Booz Allen
Claim status use case | Voicebot will use training phrases extracted from AVA submissions and Chatbot transcripts | Received claim training phrases from Shiva in January Removed PII from claims training phrases Completed intent matching for the claims status training phrases received from Chatbot transcript analysis for Nov-Dec'22 and Jan-Feb'23. | Booz Allen to review existing training phrases and finalize list. Booz Allen and VA to review and finalize intent list | Booz Allen
Notes: As user inquiries evolve, supplement training phrases: newer data, test subjects, etc
eGain data to be made available
Exploring availability of AVA data in CxDW
Step 1. train a small number of intents in dialogflow with quality training phrases. If we can achieve high classification accuracy on those intents, namely low false positives and low false negatives, that would be a and if we and let bot perform well at classifying those, with everything else
End-user input (speech) > intent classification (success determined by quality of training phrases) > bot response with relevant and approved content > end-user input >> classification of bot response
(claim status and PACT Act alone can easily grow into 10-20+ distinct intents if we pursue self-help options deeply or they could just be two intents and there are now flows, just classification and routing immediately back to cisco).
UX – content, procedures, approvals, best practices, user testing, flow design and re-design
ML – two-fold application: 1) process large datasets to generate run language models on data VA has collected that captures users’ interactions with the contact center to extract examples of end-user inquires from existing data that most closely resembles what voicebot will encouter, ensure variety utteranceslanguage models

## Slide 4: UX Workstream
Item | Description | Status | Next Steps | Owner
Content creation for Voicebot responses: re: claims | Develop content, procedures, and get approvals; documenting how Voicebot will support claims questions. | Megan finalized claim status definitions on 2/10. Team met with Regina Yount on 3/20 to discuss how VB will service intents to related to claim status timeline and estimated completion date. | Team to work on V3 of claim status Visio flow after Test session B prototype is ready and will document any changes and incorporate error strategies. Send recordings of claims content to RY and team, as well as clarified instructions of what content ideas/feedback we're looking for. | Grace/ Sunayna
Content creation for Voicebot responses: PACT Act | Learn about PACT Act and develop content responses. | Team is collaborating with Danielle to finalize new intents and confirm messaging. Danielle shared PDF of VA PACT Act Performance Dashboard. | Megan to review PACT Act content by 4/7. Team to work on V3 of PACT Act flows after prototype for Test session B is ready and will document any changes. | Grace/ Sunayna
Content for introduction messaging, errors, parameter prompts, etc. | Develop content for managing user expectations throughout conversation | Introductory/welcome content finalized by Megan on 1/27; conversational phrases finalized on 3/10. Team is writing content for options for multiple authentication failures. | Megan to finalize error messages by 3/24. Write content for multiple authentication failures. Re-submit prompts to Megan for finalization. | Grace/ Sunayna/ Nicole
User Research | Efforts to elicit design inputs from end user research and testing | Created Federal Attendee Observer sign-up spreadsheet Received information for protocols / logistics for FA at every user session | FA spreadsheet will be updated for any schedule changes Will monitor observers who signed up for sessions, arrangements to be made if no FA can be present | Nina/Ty

## Slide 5: Technology and Integration Workstreams
Item | Description | Status | Next Steps | Owner
Google DialogFlow | Implementing Voicebot solution in DialogFlow | Test environment deployed with all features relevant to User Test Session B Intent Designer hosted in BAH AWS cloud services Prototype approved by Shane | Shane to approve prototype Conduct User test session B | Josh / Nicole
VA Sandbox | A sandbox for Voicebot development | VA working on creating sandbox | Once sandbox is set-up, Booz Allen will set-up Voicebot in VA sandbox | VA
Cloud Webhook Service | Cloud Function being used for webhooks in DialogFlow | ECSO meeting held on 3/13 to review other proposals – shared with Luciana and Klay on 3/14 and 3/15, respectively Booz Allen completed requested information in CloudKey VA provided signed MOU's on 3/16 | Date TBD for next ECSO call | Booz Allen
ATO acquisition | DTC preparing for ATO | Security Assessment call occurred on 3/8 | OIS CTM ISSE team to generate Data security Categorization, will be completed by 3/29 VA to confirm Business Owner for signatory Cybersecurity Analyst to schedule FedRAMP intro meeting with vendor team after DSC | Booz Allen / VA

## Slide 6: Ad Hoc Items
Item​ | Description​ | Status​ | Next Steps​ | Owner​
Meeting with Regina | Voicebot to meet with Regina and team to share User Session A insights | Claim status timeline and phrases call occurred on 3/20 | Regina to provide POC's for determining estimated time of completion Voicebot team to provide existing content around why a claim is taking so long | Booz Allen / VA
Project Documentation | Ensuring all project documentation is accessible | Booz Allen working on Project Summary deck | Project Summary deck is being reviewed internally New resource to be used to continue to iterate on deck | Booz Allen
In-person working session | In-person working session for 6/6 & 6/7 | Finalizing plans for an in-person meeting in the DC area for June 6 and June 7 | Booz Allen to invite VA stakeholders for June 6 or June 7 for in-person meeting | Booz Allen
Review Ticket Backlog | Prioritize Backlog for team's Grooming | Review of backlog to occur on 3/29 at 10am ET | Prioritization will help drive team's Backlog Grooming and Sprint Planning meetings | Booz Allen
CX Interview | VA to provide feedback on experience / satisfaction level | Scheduled for 3/28 at 11:30am ET | Feedback gathered will help drive improvements for the project | Booz Allen / VA

## Slide 7: Open Forum
Questions / Open Discussion

## Slide 8: Appendix

## Slide 9: Project Overview
Detailed scope for Omnichannel project will be voice.
Discovery through building and learning—build it, learn from it, iterate it.
  With an overall strategy of transitioning MyVA411, transition VBA to using a Natural Language Understanding (NLU) platform.
    Determine the problem categories and point of transition.
  Through learning and understanding how self-service and triage can be supported through voice channels, assess another product which may replace AudioCARE.
  Stipulations:
    Projects must have a customer experience and Omnichannel mindset toward best customer experience for Veterans.
    Small iterative releases, solutions to run in parallel with existing solutions to Veterans are not negatively affected by our transitions.
    All products must have Veteran input.