## Slide 1
Omnichannel Voicebot Team
Booz Allen Status Meeting
December 29, 2022

## Slide 2: Agenda
ML Workstream
UX Workstream
Technology Workstream
Integration Workstream
Ad Hoc Items
Open Forum

## Slide 3: ML Workstream
Item | Description | Status | Next Steps | Owner
PACT Act use case | Voicebot will use training phrases extracted from chatbot transcripts to develop intents for classification of PACT Act-related user inquiries. | Gathered insights into ChatBot’s Pact Act intent classification and resolution Integrating insights and leveraging unique features in the data (feedback responses gathered during conversation facilitate supervised learning approaches!) to develop models for extraction of training phrases from chatbot transcripts | Align with business SMEs on the applicable level of intent granularity (at the very least, is authentication to determine eligibility in scope?) Supplement training data with insights from social media web-scraping and VSignals Generate and cluster training phrases | Millie
Claim status use case | Voicebot will use training phrases extracted from AVA submissions | VoiceBot team reviewed training phrases for status of claim provided by Kate Jira tickets #181 and #182 for uploading training phrases to Voicebot have been completed | Follow-up questions for training phrases sent to Kate on 12/20 | Booz Allen / Kate
Notes: As user inquiries evolve, supplement training phrases: newer data, test subjects, etc
eGain data to be made available
Exploring availability of AVA data in CxDW
Step 1. train a small number of intents in dialogflow with quality training phrases. If we can achieve high classification accuracy on those intents, namely low false positives and low false negatives, that would be a and if we and let bot perform well at classifying those, with everything else
End-user input (speech) > intent classification (success determined by quality of training phrases) > bot response with relevant and approved content > end-user input >> classification of bot response
(claim status and PACT Act alone can easily grow into 10-20+ distinct intents if we pursue self-help options deeply or they could just be two intents and there are now flows, just classification and routing immediately back to cisco).
UX – content, procedures, approvals, best practices, user testing, flow design and re-design
ML – two-fold application: 1) process large datasets to generate run language models on data VA has collected that captures users’ interactions with the contact center to extract examples of end-user inquires from existing data that most closely resembles what voicebot will encouter, ensure variety utteranceslanguage models

## Slide 4: UX Workstream
Item | Description | Status | Next Steps | Owner
Content creation for Voicebot responses: re: claims | Develop content, procedures, and get approvals; documenting how Voicebot will support claims questions. | Team is collaborating with Danielle to review content for general claims info. Grace submitted an issue request for support with content from Sitewide Content and IA team (ticket likely to be picked up in January). Team is diagramming claims flows in Visio. Booz Allen will work to incorporate feedback from UX testing for content. | Team to evaluate intents identified by IDPR project as candidates for Voicebot support. Align on intent determination scope beyond MyVA411 and AVA data analysis completed thus far. Booz Allen to begin meeting 2x weekly with VA.gov in January 2023. First version of claim status flow is being diagrammed. | Grace/ Sunayna
Content creation for Voicebot responses: PACT Act | Learn about PACT Act and develop content responses. | Team is collaborating with MCT on scraping user data from Social Studio to understand how Vets are talking about PACT on social media. Team is diagramming flows in Visio. | First version of PACT Act flow is being diagrammed. Booz Allen on-hold with further discussion regarding PACT Act with Danielle as business finalizes language. | Grace/ Sunayna
Content for introduction messaging, errors, parameter prompts, etc. | Develop content for setting and managing user expectations throughout the conversation flow. | Team is diagramming error flows in Visio and documenting responses to identified error categories. Team is editing content for introductions, parameters prompts, and connecting and conversational phrases. | Booz Allen will work with Danielle to finalize content for errors, introductions, conversational phrases and parameters. | Grace/ Sunayna/ Millie/ Nicole
User Research | Efforts to elicit design inputs from end user research and testing | Booz Allen completed testing on 11/16. Booz Allen completed scraping Microsoft Teams transcripts. Booz Allen completed affinity mapping | Team converting feedback into requirements. | Ty

## Slide 5: Technology Workstream
Item | Description | Status | Next Steps | Owner
Google DialogFlow | Exploring DialogFlow as a Voicebot Platform | Updated DialogFlow prototype with claim status training phrases provided by Kate Updating intent fulfillments as content is approved Using flow diagrams to determine placement of new intents and carve out new conversation possibilities | Updating DialogFlow prototype based on NCC Agent insights Add/test error events with approved content Continue investigating possible new capabilities (rate of speech, repeat, other languages, etc) | Josh / Nicole
Amazon Lex | Exploring Lex as a Voicebot Platform | Booz Allen explored Amazon Lex Booz Allen completed replicating flows in Lex Booz Allen demoed on 12/8 | N/A | Josh / Nicole

## Slide 6: Integration Workstream
Item | Description | Status | Next Steps | Owner
Integrating into Cisco IVR Telephony | Identifying how calls with transfer from IVR to Voicebot to IVR | VA is procuring DialogFlow licenses Authentication / Integration call held with Klay on 12/20 | Booz Allen to reach out to Trish Dang, Regina Yount, and Brenda Torress-Hill for authentication methods Voicebot could use In New Year, establish regular cadence with Klay and team for updates and continued progress. | Booz Allen

## Slide 7: Ad Hoc Items
Item​ | Description​ | Status​ | Next Steps​ | Owner​
Project Documentation | Ensuring all project documentation is accessible | Booz Allen completed upload of research and work to Github Includes data analysis, overview of API's / systems for integration, flows, etc. Booz Allen working on Project Summary deck | Project Summary deck is being reviewed internally UX slides needed updating, based on conclusion of User Session A | Booz Allen
ATO acquisition | DTC preparing for ATO | Booz Allen completed Data Elements and PTA, sent on 12/15 | POC portion in PTA not completed. For Booz Allen to complete, we would need POC for VA ISSO | Booz Allen
Commercial Competitive Analysis | Commercial Competitive Analysis | Team is calling NLU IVR's to explore IVR features / good experiences Team updated MURAL by organizing stickies per company, grouping per platform | Team to continue exploring and updating MURAL | Booz Allen

## Slide 8: Open Forum
Open discussion

## Slide 9: Appendix

## Slide 10: Project Overview
Detailed scope for Omnichannel project will be voice.
Discovery through building and learning—build it, learn from it, iterate it.
  With an overall strategy of transitioning MyVA411, transition VBA to using a Natural Language Understanding (NLU) platform.
    Determine the problem categories and point of transition.
  Through learning and understanding how self-service and triage can be supported through voice channels, assess another product which may replace AudioCARE.
  Stipulations:
    Projects must have a customer experience and Omnichannel mindset toward best customer experience for Veterans.
    Small iterative releases, solutions to run in parallel with existing solutions to Veterans are not negatively affected by our transitions.
    All products must have Veteran input.