## Slide 1
Voicebot
Booz Allen Status Meeting
May 25, 2023

## Slide 2: Agenda
ML Workstream
UX Workstream
Technology Workstream
Integration Workstream
Ad Hoc Items
Open Forum

## Slide 3: ML Workstream
Item | Description | Status | Next Steps | Owner
PACT Act use case | Voicebot will use training phrases extracted from Chatbot transcripts, reddit and survey data to develop intents for classification of PACT Act-related user inquiries. | Completed intent matching for the PACT Act training phrases received from Kate, PACT Survey and Chatbot transcript analysis for Nov-Dec'22 and Jan-Feb'23 and Reddit data. Working on SOP for a. to manage the inflow of new data and version control older data b. to standardize the process of intent matching as much as possible c. to integrate with intent designer tool. | Booz Allen to Analyze Chatbot Transcript for March’23. Booz Allen to start restructuring the Pact Act Track in Google Dialog flow based on user and team testing results. VA to provide Training Phrases from IDPR work. | Booz Allen
Claim status use case | Voicebot will use training phrases extracted from AVA submissions, Chatbot transcripts, reddit and survey data to develop intents for classification of claim related user inquiries. | Completed intent matching for the claims status training phrases received from Chatbot transcript analysis for Nov-Dec'22 and Jan-Feb'23 and Reddit data. improving accuracy and overall performance of the Voicebot Completed analyzing utterances received from Test Session B. | Booz Allen to perform review to improve accuracy and performance of the Voicebot. Booz Allen to start restructuring the Google Dialog flow based on user and team testing results. VA to provide Training Phrases from IDPR work. | Booz Allen
Social Media Listening | Booz Allen to explore possibility of leveraging social studio for Voicebot. | Began exploration into digital learning Booz Allen got log in Instructions for Social Studio. | Awaiting historical PACT Act data from Salesforce. | Booz Allen
Notes: As user inquiries evolve, supplement training phrases: newer data, test subjects, etc
eGain data to be made available
Exploring availability of AVA data in CxDW
Step 1. train a small number of intents in dialogflow with quality training phrases. If we can achieve high classification accuracy on those intents, namely low false positives and low false negatives, that would be a and if we and let bot perform well at classifying those, with everything else
End-user input (speech) > intent classification (success determined by quality of training phrases) > bot response with relevant and approved content > end-user input >> classification of bot response
(claim status and PACT Act alone can easily grow into 10-20+ distinct intents if we pursue self-help options deeply or they could just be two intents and there are now flows, just classification and routing immediately back to cisco).
UX – content, procedures, approvals, best practices, user testing, flow design and re-design
ML – two-fold application: 1) process large datasets to generate run language models on data VA has collected that captures users’ interactions with the contact center to extract examples of end-user inquires from existing data that most closely resembles what voicebot will encouter, ensure variety utteranceslanguage models

## Slide 4: UX Workstream
Item | Description | Status | Next Steps | Owner
Content creation for Voicebot responses: re: claims | Develop content, procedures, and get approvals; documenting how Voicebot will support claims questions. | VA.gov Github file created to build VB content style recommendations and notes. Claims content edited by Megan on 5/12. | Populate content into Intent Designer. Edit content based upon restructured path on Google Dialog Flow to accommodate proposed changes. | Grace/ Sunayna
Content creation for Voicebot responses: PACT Act | Learn about PACT Act and develop content responses. | Working with devs, UX, and ML to improve PACT experience through more defined flows/tracks and prompting questions. | Continue refining PACT Act content. Start curating content based on the restructured Pact Act Track in Google Dialog flow to accommodate the findings from user and team testing results. | Grace/ Sunayna
Content for introduction messaging, errors, parameter prompts, etc. | Develop content for managing user expectations throughout conversation | Writing content for a “help menu” intent. Attended VA.gov's Content CoP error message retreat on 5/17 to keep awareness of VA.gov Design System changes. | Edit content based on any insights from Test Session C findings. | Grace/ Sunayna
UX Design & Strategy | Efforts to elicit design inputs from end user research and testing | Completed data synthesis and analysis on Test Session C findings 5/22 Began working on HWM statements and actionable items for Test Session C Continued discussions with the Dev workstream to ideate on potential feature prioritization and capabilities Continued Prep & Discussion for User Test Session D Began initial planning for User Interface creation on Intent Designer | Complete User Test Session C HMW statements Continue User Interface preparation for Intent Designer tool Continue prep/planning of User Test Session D | Julie/Ty

## Slide 5: Technology and Integration Workstreams
Item | Description | Status | Next Steps | Owner
Google DialogFlow | Implementing Voicebot solution in DialogFlow | Allow for content mappings to intent, location, and webhooks within Dialogflow in intent designer Working with UX, ML and content to devise a better structure for drilling down on questions Splitting up PACT into its own flow to allow more back and forth with the voicebot. Implementing eligibility intake to better capture service record Implement help menu to bridge knowledge gaps and increase maneuverability within the voicebot | Improve similarity matching algorithm Assign locations to content added in intent designer Use intent designer as new source of record for content Further develop claims and pact act as separate flows | Josh / Nicole
Cloud Webhook Service | Cloud Function being used for webhooks in DialogFlow | Technical Review Meeting held on 4/28 | ECSO cloud approved, in process of being acquired | Josh
VA Sandbox | A sandbox for Voicebot development | VA has created sandbox | Booz Allen exploring sandbox | Josh
ATO acquisition | DTC preparing for ATO | Project identified as moderate risk | ATO timeline TBD | VA

## Slide 6: Ad Hoc Items
Item​ | Description​ | Status​ | Next Steps​ | Owner​
In-person working session | In-person working session for 6/6 & 6/7 | Agenda reviewed on 5/23 | Next planning session scheduled for 5/31 | Booz Allen

## Slide 7: Open Forum
Questions / Open Discussion

## Slide 8: Appendix

## Slide 9: Project Overview
Detailed scope for Omnichannel project will be voice.
Discovery through building and learning—build it, learn from it, iterate it.
  With an overall strategy of transitioning MyVA411, transition VBA to using a Natural Language Understanding (NLU) platform.
    Determine the problem categories and point of transition.
  Through learning and understanding how self-service and triage can be supported through voice channels, assess another product which may replace AudioCARE.
  Stipulations:
    Projects must have a customer experience and Omnichannel mindset toward best customer experience for Veterans.
    Small iterative releases, solutions to run in parallel with existing solutions to Veterans are not negatively affected by our transitions.
    All products must have Veteran input.

## Slide 10: UX Testing Session B
Highlights
Other Commonalities
Thank You For Your Service
"It made me smile. It was kind of cheesy, but I appreciated it."
"My first thought would be, why is it computer telling me that? It doesn't really care."
User-Specific Information: Claims & PACT Act
"How do I know that I was affected by this?...my question would be like, what am I supposed to do?"
Trouble trusting the bot to handle complex questions;
Unease during wait times & desire for computing indications;
Need advice on next steps or missing information;
User-specific PACT act information;
Ability to locating user-specific VA healthcare sites & appointments