## Slide 1
Voicebot
Booz Allen Status Meeting
July 6, 2023

## Slide 2: Agenda
ML Workstream
UX Workstream
Technology Workstream
Integration Workstream
Ad Hoc Items
Open Forum
UC Meeting – July 19 & July 20 - Discussion

## Slide 3: ML Workstream
Item | Description | Status | Next Steps | Owner
PACT Act and Disability Claims use case | Voicebot will use training phrases extracted from Chatbot transcripts, reddit and survey (for PACT), and AVA data to develop intents for classification of PACT Act and disability claim related user inquiries. | Completed intent matching for the PACT Act and claims training phrases received from Kate, PACT Survey and Chatbot transcript analysis for Nov-Dec'22 and Jan-Feb'23 and Reddit data. Working on restructuring the Pact Act Track in Google Dialog flow based on user and team testing results. Booz Allen is working to gather training phrases for no more questions, agent transfer, help menu and return to main menu intents. Completed user.can_you_repeat Training Phrases. | Booz Allen to Analyze Chatbot Transcript for March ’23. Booz Allen to carve out smaller PACT Flows to support content chunking and to better guide the callers. Building toxic exposure flow to support related intents and test training phrases. Booz Allen is beginning exploration phase of VCL routing abilities, including gathering training phrases from various sources. Booz Allen in working on Tell Me More track to be placed in the flows | Booz Allen
Social Media Listening | Booz Allen to explore possibility of leveraging social studio for Voicebot. | Began exploration into digital learning Booz Allen got log in Instructions for Social Studio. | Awaiting historical PACT Act data from Salesforce. | Booz Allen
Notes: As user inquiries evolve, supplement training phrases: newer data, test subjects, etc
eGain data to be made available
Exploring availability of AVA data in CxDW
Step 1. train a small number of intents in dialogflow with quality training phrases. If we can achieve high classification accuracy on those intents, namely low false positives and low false negatives, that would be a and if we and let bot perform well at classifying those, with everything else
End-user input (speech) > intent classification (success determined by quality of training phrases) > bot response with relevant and approved content > end-user input >> classification of bot response
(claim status and PACT Act alone can easily grow into 10-20+ distinct intents if we pursue self-help options deeply or they could just be two intents and there are now flows, just classification and routing immediately back to cisco).
UX – content, procedures, approvals, best practices, user testing, flow design and re-design
ML – two-fold application: 1) process large datasets to generate run language models on data VA has collected that captures users’ interactions with the contact center to extract examples of end-user inquires from existing data that most closely resembles what voicebot will encouter, ensure variety utteranceslanguage models

## Slide 4: UX Workstream
Item | Description | Status | Next Steps | Owner
Content creation for Voicebot responses: claims and PACT Act | Develop content, procedures, and get approvals; documenting how Voicebot will support claims and PACT Act questions. | Implementing identified CX must-haves for Test Session D including "chunking" content for toxic exposure-related intents. Let's clarify "tell me more" intent: discussion. | Collaborate and align with other teams working on content structuring to ensure consistency (Danielle to connect with LM). | Grace/ Sunayna
Content for introduction, errors, parameter prompts, etc. | Develop content for managing user expectations throughout conversation | Refining content for a “help menu” intent. | Edit content based on any insights from Test Session C findings. Test help menu intent & content. | Grace/ Sunayna
UX Design & Strategy | Efforts to elicit design inputs from end user research and testing | Continue synthesizing the creation of a findings deck for User Test Session C Performed a UX collaborative session to discuss "How To" For Test Session D Collaborative sessions with the workstreams for "How To" sessions and idea generation Continued design for the User Interface on Intent Designer | User Test Session C findings briefing Continue with Test Session D creation/collaboration sessions Create Test Session D Rough Draft after collaborative sessions Continue User Interface design for Intent Designer tool | Julie/Ty

## Slide 5: Technology and Integration Workstreams
Item | Description | Status | Next Steps | Owner
Google DialogFlow | Implementing Voicebot solution in DialogFlow | Finalizing first pass at toxic exposure track in DF with more guided selection options and prompts for more info Investigating latency around DF response times – tracking response times with different end of speech values. | Meet with Google On July 14 with list of discovery questions that came out of in-person. Work towards a testable prototype for Test Session D Meet with UX to confer on test plans for Session D. Further flesh out toxic exposure track within Pact flow – determine related intents, context-specific help, etc. | Josh / Nicole
Cloud Webhook Service | Cloud Function being used for webhooks in DialogFlow | Technical Review Meeting held on 4/28 | ECSO cloud approved, in process of being acquired ECSO call scheduled for July 6 at 2:30pm ET | VA
VA Sandbox | A sandbox for Voicebot development | VA has created sandbox | Booz Allen exploring sandbox | Josh
ATO acquisition | DTC preparing for ATO | Project identified as moderate risk | ATO timeline TBD | VA

## Slide 6: Ad Hoc
Item | Description | Status | Next Steps | Owner
Deliverables from June In-Person | Ways of Working and Team Charter | Team began work on Ways of Working and Team Charter | Both to be completed by mid-July | Robyn
VBA In-Person | Meeting with VBA to review scope and questions | Team reviewed use cases and generated list of questions Space reserved at Booz Allen DC office for Monday 8/21 – Wednesday 8/23 Space reserved at Booz Allen McLean office for Wednesday 8/23 – Friday 8/25 | Regina to share with us her availability for July and August | Gian
UC virtual meeting | Meeting with UC to walkthrough integration & authentication questions | Call held on 6/27 to discuss virtual meeting with UC | Team to share potential agenda / list of items to be discussed today, 7/6 | Gian
VCL meeting with Dr. Foreman | Meeting with VCL to discuss Voicebot opportunities | Voicebot ready to engage with Dr. Foreman to discuss crisis-management | Call scheduled for 8/17 | VA
USPS Contact | Meeting with USPS to ask implementation questions | Team prepared questions for USPS | Kate to schedule call with USPS POC | VA

## Slide 7: Open Forum
Questions / Open Discussion

## Slide 8: Appendix

## Slide 9: Project Overview
Detailed scope for Omnichannel project will be voice.
Discovery through building and learning—build it, learn from it, iterate it.
  With an overall strategy of transitioning MyVA411, transition VBA to using a Natural Language Understanding (NLU) platform.
    Determine the problem categories and point of transition.
  Through learning and understanding how self-service and triage can be supported through voice channels, assess another product which may replace AudioCARE.
  Stipulations:
    Projects must have a customer experience and Omnichannel mindset toward best customer experience for Veterans.
    Small iterative releases, solutions to run in parallel with existing solutions to Veterans are not negatively affected by our transitions.
    All products must have Veteran input.

## Slide 10: UX Testing Session B
Highlights
Other Commonalities
Thank You For Your Service
"It made me smile. It was kind of cheesy, but I appreciated it."
"My first thought would be, why is it computer telling me that? It doesn't really care."
User-Specific Information: Claims & PACT Act
"How do I know that I was affected by this?...my question would be like, what am I supposed to do?"
Trouble trusting the bot to handle complex questions;
Unease during wait times & desire for computing indications;
Need advice on next steps or missing information;
User-specific PACT act information;
Ability to locating user-specific VA healthcare sites & appointments