## Slide 1
Omnichannel Voicebot Team
Booz Allen Status Meeting
November 17, 2022

## Slide 2: Agenda
ML Workstream
UX Workstream
Technology Workstream
Integration Workstream
Ad Hoc Items
Open Forum

## Slide 3: ML Workstream
Item | Description | Status | Next Steps | Owner
Claim status use case | Intent determination project to provide labeled training phrases that Voicebot will learn from. The data will elucidate the complexity and granularity of user inquiries, and ensure we capture the variety of ways users express the same intent. | Training phrases obtained from VA411 agent notes are being labeled but not yet shared with Voicebot. More training phrases are being extracted from chat transcripts and AVA | Decide if there are any sub-intents we can/want Voicebot to resolve, if any. If none, and we will just route everyone to NCC gen skill group, we would train the bot accordingly. | Millie/Nicole
PACT Act use case | We are waiting on labeled training phrases that Voicebot will learn from to classify and assist with PACT Act related inquiries. | We will need to identify the gaps that will inevitably exist. | Booz Allen to continue collaboration meetings with Danielle for claim status information, general claim information, PACT Act and error messages. | Millie/Nicole
Notes: eGain data to be made available
Exploring availability of AVA data in CxDW
Step 1. train a small number of intents in dialogflow with quality training phrases. If we can achieve high classification accuracy on those intents, namely low false positives and low false negatives, that would be a and if we and let bot perform well at classifying those, with everything else
End-user input (speech) > intent classification (success determined by quality of training phrases) > bot response with relevant and approved content > end-user input >> classification of bot response
(claim status and PACT Act alone can easily grow into 10-20+ distinct intents if we pursue self-help options deeply or they could just be two intents and there are now flows, just classification and routing immediately back to cisco).
UX – content, procedures, approvals, best practices, user testing, flow design and re-design
ML – two-fold application: 1) process large datasets to generate run language models on data VA has collected that captures users’ interactions with the contact center to extract examples of end-user inquires from existing data that most closely resembles what voicebot will encouter, ensure variety utteranceslanguage models

## Slide 4: UX Workstream
Item | Description | Status | Next Steps | Owner
Content research and creation for Voicebot responses: re: claims | Develop content, procedures, and get approvals. Documenting how Voicebot will support claims questions. | Use NCC agent scripts on VA intranet as starting point and map those responses to our intents. Booz Allen is in collaboration with Danielle to review custom content responses for general claims information and claims status. | Team to evaluate intents identified by IDPR project as candidates for Voicebot support. Align on intent determination scope beyond MyVA411 and AVA data analysis completed thus far. Booz Allen is working to incorporate comments/ feedback from collaboration with VA.gov. | Grace/ Sunayna
Content creation for Voicebot responses: PACT Act | Learn about PACT Act and develop content responses. | Booz Allen held call on 11/9 with Danielle to collaborate on PACT Act custom responses. Danielle shared MURAL with PACT Act wording as VA.gov finalizes content. | Booz Allen will continue collaboration meetings with Danielle for PACT Act content. | Grace
Error management | Develop a high-level strategy for classifying and handling errors. | Researching best practices for error handling and messaging using DialogFlow CX error concepts and VA.gov Design System. Matching different types of errors with corresponding error messaging content. | Booz Allen will develop error flows in DialogFlow and Lex. Booz Allen will work with Danielle to create and finalize error messages/content. | Grace/ Sunayna/ Millie/ Nicole
Usability testing | Preparation for initial testing | Booz Allen is running usability testing with agents | Booz Allen to scrape Teams transcripts for relevant feedback At conclusion of testing, team will use feedback to document proposed changes to Voicebot | Julie / Ty

## Slide 5: Technology Workstream
Item | Description | Status | Next Steps | Owner
Google DialogFlow | Exploring DialogFlow as a Voicebot Platform | Booz Allen created Google Cloud sandboxes on Booz Allen side to begin DialogFlow learning Booz Allen demoed Claims and PACT Act flows in DialogFlow on 11/4 | VA working on creating a Google Cloud sandbox Booz Allen exploring call metrics and log capabilitie | VA / Josh
Amazon Lex | Exploring Lex as a Voicebot Platform | A Booz Allen AWS sandbox set-up Booz Allen focused on getting access to AWS | Booz Allen to explore Amazon Lex Booz Allen to replicate flows from DialogFlow | Josh / Nicole
ATO Process | Learning about ATO process | VA determined Voicebot could not use existing BAM Moderate ATO Booz Allen submitted PTA to VA on 11/1 | ATO call scheduled for 11/3 with Google, VA and Booz Allen | Booz Allen

## Slide 6: Integration Workstream
Item | Description | Status | Next Steps | Owner
API's | Investigating APIs that expose claims data | Obtained VA access to APIs to investigate responses Booz Allen to documented relevant fields returned from API calls | Booz Allen reviewing relevant fields to use for existing and future workflows | Josh/Nicole
Integrating into Cisco IVR Telephony | Identifying how calls with transfer from IVR to Voicebot to IVR | Cisco demoed DialogFlow integrated into Cisco IVR on 11/2 | Klay and Christian to provide NCC branch for team's development VA IVR team to set up sandbox for Booz Allen – status unknown VA and Booz Allen to identify if Booz Allen GDP sandbox will be used to connect to IVR Booz Allen to begin ESECC request process once preferred sandbox identified | Josh/Nicole

## Slide 7: Ad Hoc Items
Item​ | Description​ | Status​ | Next Steps​ | Owner​
Project Documentation | Ensuring all project documentation is accessible | Booz Allen ensuring all completed work during PoP has been documented, uploaded to Github Includes data analysis, overview of API's / systems for integration, flows, etc. | Booz Allen to create PowerPoint deck which communicates completed work, and location in Github | Booz Allen
Demoing Voicebot | Establishing cadence to demo Voicebot to stakeholders | Nicole and Josh demoed Voicebot in DialogFlow on 11/4 | Determining cadence for demos to stakeholders | Booz Allen / VA
Jira | Setting up Jira as team ticketing system | Booz Allen setting up Jira, transitioning away from Zenhub Backlog Grooming occurred on 11/9 | Get access for Luciana, Kate, and Nina | Booz Allen
1:1's with Luciana | 1:1's with Luciana | Luciana offered voluntary 1:1 meetings with Booz Allen | Booz Allen to reach out to Luciana for 1:1's | Booz Allen
Commercial Competitive Analysis | Commercial Competitive Analysis | Francisco provided POC for USPS Mike provided list of state agencies using DialogFlow Documenting companies which use an NLU IVR | Mike Snodgrass to provide POC's for state agencies using DialogFlow VA to reach out to POC's for other known projects using DialogFlow | Gian / VA

## Slide 8: Open Forum
Open discussion

## Slide 9: Appendix

## Slide 10: Project Overview
Detailed scope for Omnichannel project will be voice.
Discovery through building and learning—build it, learn from it, iterate it.
  With an overall strategy of transitioning MyVA411, transition VBA to using a Natural Language Understanding (NLU) platform.
    Determine the problem categories and point of transition.
  Through learning and understanding how self-service and triage can be supported through voice channels, assess another product which may replace AudioCARE.
  Stipulations:
    Projects must have a customer experience and Omnichannel mindset toward best customer experience for Veterans.
    Small iterative releases, solutions to run in parallel with existing solutions to Veterans are not negatively affected by our transitions.
    All products must have Veteran input.