## Slide 1
Omnichannel Voicebot Team
Booz Allen Status Meeting
January 12, 2023

## Slide 2: Agenda
ML Workstream
UX Workstream
Technology Workstream
Integration Workstream
Ad Hoc Items
Open Forum

## Slide 3: ML Workstream
Item | Description | Status | Next Steps | Owner
PACT Act use case | Voicebot will use training phrases extracted from Chatbot transcripts to develop intents for classification of PACT Act-related user inquiries. | Leveraging already identified clustered phrases for PACT Act from Chatbot transcripts Reviewing PACT Act responses from VSignals | Review training phrases to match those which support existing intents With remaining training phrases, create additional intents / responses where needed Create training phrases from VSignals responses | Booz Allen
Claim status use case | Voicebot will use training phrases extracted from AVA submissions and Chatbot transcripts | Reviewed training phrases for status of claim provided by Kate Jira tickets #181 and #182 for uploading training phrases to Voicebot have been completed Received claim training phrases from Shiva | Reviewing training phrases for possible use for Voicebot Training phrases to be tested during User Session B | Booz Allen
Notes: As user inquiries evolve, supplement training phrases: newer data, test subjects, etc
eGain data to be made available
Exploring availability of AVA data in CxDW
Step 1. train a small number of intents in dialogflow with quality training phrases. If we can achieve high classification accuracy on those intents, namely low false positives and low false negatives, that would be a and if we and let bot perform well at classifying those, with everything else
End-user input (speech) > intent classification (success determined by quality of training phrases) > bot response with relevant and approved content > end-user input >> classification of bot response
(claim status and PACT Act alone can easily grow into 10-20+ distinct intents if we pursue self-help options deeply or they could just be two intents and there are now flows, just classification and routing immediately back to cisco).
UX – content, procedures, approvals, best practices, user testing, flow design and re-design
ML – two-fold application: 1) process large datasets to generate run language models on data VA has collected that captures users’ interactions with the contact center to extract examples of end-user inquires from existing data that most closely resembles what voicebot will encouter, ensure variety utteranceslanguage models

## Slide 4: UX Workstream
Item | Description | Status | Next Steps | Owner
Content creation for Voicebot responses: re: claims | Develop content, procedures, and get approvals; documenting how Voicebot will support claims questions. | Team is collaborating with Danielle on claims content strategy. Booz Allen held introductory meeting with Megan Zehnder, a copy editor from Sitewide Content team, to discuss further content support. Team is diagramming claims flows in Visio and incorporating feedback from UX testing into content. | Team to evaluate intents identified by IDPR project as candidates for Voicebot support. Align on intent determination scope beyond MyVA411 and AVA data analysis completed thus far. Booz Allen to create copy editing schedule and content documentation for Megan. | Grace/ Sunayna
Content creation for Voicebot responses: PACT Act | Learn about PACT Act and develop content responses. | Team is working with MCT to get access to Social Studio to scrape user data about PACT. Team is collaborating with Danielle on PACT content strategy. Team is diagramming flows in Visio. | Booz Allen to create copy editing schedule and content documentation for Megan. | Grace/ Sunayna
Content for introduction messaging, errors, parameter prompts, etc. | Develop content for setting and managing user expectations throughout the conversation flow. | Team is diagramming error flows in Visio and documenting responses to identified error categories. Team is editing content for introductions, parameters prompts, and connecting and conversational phrases. | Booz Allen to create copy editing schedule and content documentation for Megan. | Grace/ Sunayna/ Nicole
User Research | Efforts to elicit design inputs from end user research and testing | Requirements were created for insights gathered in User Session A | Booz Allen to present findings on 1/12 Team met on 1/10 to brainstorm User Session B | Julie

## Slide 5: Technology Workstream
Item | Description | Status | Next Steps | Owner
Google DialogFlow | Exploring DialogFlow as a Voicebot Platform | Updated DialogFlow prototype with claim status training phrases provided by Kate Updating intent fulfillments as content is approved Using flow diagrams to determine placement of new intents and carve out new conversation possibilities | Updating DialogFlow prototype based on requirements from insights gathered in User Session A Add/test error events with approved content Continue investigating possible new capabilities (rate of speech, repeat, other languages, etc) | Josh / Nicole

## Slide 6: Integration Workstream
Item | Description | Status | Next Steps | Owner
Integrating into Cisco IVR Telephony | Identifying how calls with transfer from IVR to Voicebot to IVR | VA is procuring DialogFlow licenses Authentication / Integration call held with Klay on 12/20 Email sent to Trish Dang, Regina Yount, and Brenda Torress-Hill for authentication methods for Voicebot | Call scheduled with Klay for 1/17 for monthly touch base Waiting for response from authentication methods | Booz Allen
VA Sandbox | A sandbox Voicebot development | VA working on creating sandbox | Once sandbox is set-up, Booz Allen will set-up Voicebot and begin exploring integration into VA services | VA

## Slide 7: Ad Hoc Items
Item​ | Description​ | Status​ | Next Steps​ | Owner​
Seamless Experience Workshop | Discuss Voicebot vision and Omnichannel experience | Booz Allen discussing future capabilities / vision for Voicebot Met with Luciana on 1/10 to go over project vision | Create deck and prepare for meeting | Booz Allen
ATO acquisition | DTC preparing for ATO | Booz Allen completed Data Elements and PTA, sent on 12/15 | ATO approval estimated to take 8-12 months | Booz Allen
Project Documentation | Ensuring all project documentation is accessible | Booz Allen completed upload of research and work to Github Includes data analysis, overview of API's / systems for integration, flows, etc. Booz Allen working on Project Summary deck | Project Summary deck is being reviewed internally UX slides needed updating, based on conclusion of User Session A | Booz Allen

## Slide 8: Open Forum
User Session A findings

## Slide 9: Appendix

## Slide 10: Project Overview
Detailed scope for Omnichannel project will be voice.
Discovery through building and learning—build it, learn from it, iterate it.
  With an overall strategy of transitioning MyVA411, transition VBA to using a Natural Language Understanding (NLU) platform.
    Determine the problem categories and point of transition.
  Through learning and understanding how self-service and triage can be supported through voice channels, assess another product which may replace AudioCARE.
  Stipulations:
    Projects must have a customer experience and Omnichannel mindset toward best customer experience for Veterans.
    Small iterative releases, solutions to run in parallel with existing solutions to Veterans are not negatively affected by our transitions.
    All products must have Veteran input.