## Slide 1
Voicebot
Booz Allen Status Meeting
March 16, 2023

## Slide 2: Agenda
ML Workstream
UX Workstream
Technology Workstream
Integration Workstream
Ad Hoc Items
Open Forum

## Slide 3: ML Workstream
Item | Description | Status | Next Steps | Owner
PACT Act use case | Voicebot will use training phrases extracted from Chatbot transcripts to develop intents for classification of PACT Act-related user inquiries. | Completed intent matching for the PACT Act training phrases received from Kate. Completed grouping responses from PACT Act Survey. Completed intent matching for the PACT Act training phrases received from Chatbot transcript analysis for Nov-Dec'22 and Jan-Feb'23. | Booz Allen to review existing training phrases and finalize list. Booz Allen and VA to review and finalize intent list | Booz Allen
Claim status use case | Voicebot will use training phrases extracted from AVA submissions and Chatbot transcripts | Received claim training phrases from Shiva in January Removed PII from claims training phrases Completed intent matching for the claims status training phrases received from Chatbot transcript analysis for Nov-Dec'22 and Jan-Feb'23. | Booz Allen to review existing training phrases and finalize list. Booz Allen and VA to review and finalize intent list | Booz Allen
Notes: As user inquiries evolve, supplement training phrases: newer data, test subjects, etc
eGain data to be made available
Exploring availability of AVA data in CxDW
Step 1. train a small number of intents in dialogflow with quality training phrases. If we can achieve high classification accuracy on those intents, namely low false positives and low false negatives, that would be a and if we and let bot perform well at classifying those, with everything else
End-user input (speech) > intent classification (success determined by quality of training phrases) > bot response with relevant and approved content > end-user input >> classification of bot response
(claim status and PACT Act alone can easily grow into 10-20+ distinct intents if we pursue self-help options deeply or they could just be two intents and there are now flows, just classification and routing immediately back to cisco).
UX – content, procedures, approvals, best practices, user testing, flow design and re-design
ML – two-fold application: 1) process large datasets to generate run language models on data VA has collected that captures users’ interactions with the contact center to extract examples of end-user inquires from existing data that most closely resembles what voicebot will encouter, ensure variety utteranceslanguage models

## Slide 4: UX Workstream
Item | Description | Status | Next Steps | Owner
Content creation for Voicebot responses: re: claims | Develop content, procedures, and get approvals; documenting how Voicebot will support claims questions. | Megan finalized claim status definitions on 2/10. | Team to work on V3 of claim status flow in Visio after prototype for Test session B is ready and will document any changes and incorporate error strategies. Team to meet with Regina Yount on 3/20 to discuss how VB will service the claims status experience. | Grace/ Sunayna
Content creation for Voicebot responses: PACT Act | Learn about PACT Act and develop content responses. | Team is collaborating with Danielle to finalize new intents and confirm messaging. Danielle shared PDF of VA PACT Act Performance Dashboard. | Megan to review PACT Act content by 4/7. Team to work on V3 of PACT Act flows after prototype for Test session B is ready and will document any changes and incorporate error strategies. | Grace/ Sunayna
Content for introduction messaging, errors, parameter prompts, etc. | Develop content for managing user expectations throughout conversation | Introductory/welcome content finalized by Megan on 1/27. Authentication prompts rewritten to include option for keypad input. Conversational phrases finalized on 3/10. | Megan error messages by 3/24. Re-submit prompts to Megan for finalization. Write content for confirming data during authentication. | Grace/ Sunayna/ Nicole
User Research | Efforts to elicit design inputs from end user research and testing | Each team member tested Voicebot and provided feedback to developers Submitted User Test Plan B along with prototype phone number to Shane for final review & rough draft of a Post-session questionnaire; Shane approved User Test Plan and has formally kicked-off the recruitment process with Perigean. | UX team to prep questions for Perigean meeting Perigean is investigating possibility to make calls during a Zoom call we will have more information on Friday after our meeting | Nina/Ty

## Slide 5: Technology and Integration Workstreams
Item | Description | Status | Next Steps | Owner
Google DialogFlow | Implementing Voicebot solution in DialogFlow | Test environment deployed with all features relevant to User Test Session B Building application which will assist in maintaining training phrases in a single place for dev consumption and efficient inputting into DF Working on getting Intent Designer hosted internally | Shane to approve prototype Conduct User test session B | Josh / Nicole
VA Sandbox | A sandbox for Voicebot development | VA working on creating sandbox | Once sandbox is set-up, Booz Allen will set-up Voicebot in VA sandbox | VA
Cloud Webhook Service | Cloud Function being used for webhooks in DialogFlow | Unified Communications Infrastructure team confirmed approach with ECSO on 3/9 call ECSO meeting held on 3/13 to review other proposals – shared with Luciana and Klay on 3/14 and 3/15, respectively Booz Allen completed requested information in CloudKey | Booz Allen to confirm decision for DialogFlow and AWS GovCloud by end of the week VA reviewing MOU's for signature | Booz Allen
ATO acquisition | DTC preparing for ATO | Security Assessment call occurred on 3/8 | OIS CTM ISSE team to generate Data security Categorization, will be completed by 3/29 VA to confirm Business Owner for signatory Cybersecurity Analyst to schedule FedRAMP intro meeting with vendor team after DSC | Booz Allen / VA

## Slide 6: Ad Hoc Items
Item​ | Description​ | Status​ | Next Steps​ | Owner​
Meeting with Regina | Voicebot to meet with Regina and team to share User Session A insights | Authentication data points agreed upon in 3/9 call with VBA Call metrics / data sources call agreed upon in 3/13 call with VBA | Claim status timeline and phrases scheduled for 3/20 at 2pm ET | Booz Allen
Project Documentation | Ensuring all project documentation is accessible | Booz Allen working on Project Summary deck | Project Summary deck is being reviewed internally New resource to be used to continue to iterate on deck | Booz Allen

## Slide 7: Open Forum
Questions / Open Discussion

## Slide 8: Appendix

## Slide 9: Project Overview
Detailed scope for Omnichannel project will be voice.
Discovery through building and learning—build it, learn from it, iterate it.
  With an overall strategy of transitioning MyVA411, transition VBA to using a Natural Language Understanding (NLU) platform.
    Determine the problem categories and point of transition.
  Through learning and understanding how self-service and triage can be supported through voice channels, assess another product which may replace AudioCARE.
  Stipulations:
    Projects must have a customer experience and Omnichannel mindset toward best customer experience for Veterans.
    Small iterative releases, solutions to run in parallel with existing solutions to Veterans are not negatively affected by our transitions.
    All products must have Veteran input.