## Slide 1
Voicebot
Booz Allen Status Meeting
February 9, 2023

## Slide 2: Agenda
ML Workstream
UX Workstream
Technology Workstream
Integration Workstream
Ad Hoc Items
Open Forum

## Slide 3: ML Workstream
Item | Description | Status | Next Steps | Owner
PACT Act use case | Voicebot will use training phrases extracted from Chatbot transcripts to develop intents for classification of PACT Act-related user inquiries. | Completed clustering and mapping of PACT Act utterances from ChatBot transcripts Reviewed clustering of VSignal responses and assign to intent, upload to Voicebot | Team to review intents to decide which ones will be supported by Voicebot Identified intents will be sent to VA Ticket #258 created to upload clusters from Signals Review unique PACT Act utterances from Chatbot transcripts from January | Booz Allen
Claim status use case | Voicebot will use training phrases extracted from AVA submissions and Chatbot transcripts | Reviewed training phrases for status of claim provided by Kate Jira tickets #181 and #182 for uploading training phrases to Voicebot have been completed Received claim training phrases from Shiva | Training phrases to be tested during User Session B | Booz Allen
Notes: As user inquiries evolve, supplement training phrases: newer data, test subjects, etc
eGain data to be made available
Exploring availability of AVA data in CxDW
Step 1. train a small number of intents in dialogflow with quality training phrases. If we can achieve high classification accuracy on those intents, namely low false positives and low false negatives, that would be a and if we and let bot perform well at classifying those, with everything else
End-user input (speech) > intent classification (success determined by quality of training phrases) > bot response with relevant and approved content > end-user input >> classification of bot response
(claim status and PACT Act alone can easily grow into 10-20+ distinct intents if we pursue self-help options deeply or they could just be two intents and there are now flows, just classification and routing immediately back to cisco).
UX – content, procedures, approvals, best practices, user testing, flow design and re-design
ML – two-fold application: 1) process large datasets to generate run language models on data VA has collected that captures users’ interactions with the contact center to extract examples of end-user inquires from existing data that most closely resembles what voicebot will encouter, ensure variety utteranceslanguage models

## Slide 4: UX Workstream
Item | Description | Status | Next Steps | Owner
Content creation for Voicebot responses: re: claims | Develop content, procedures, and get approvals; documenting how Voicebot will support claims questions. | Team is collaborating with Danielle and Megan on claims content strategy. Team is diagramming claims flows in Visio and incorporating feedback from UX testing into content. | Megan to review claim status definitions by 2/10. | Grace/ Sunayna
Content creation for Voicebot responses: PACT Act | Learn about PACT Act and develop content responses. | Team is scraping social media for Veteran questions. Team is collaborating with Danielle on PACT content strategy. | Form content around scraped questions. Megan to review content and provide feedback according to schedule. | Grace/ Sunayna
Content for introduction messaging, errors, parameter prompts, etc. | Develop content for managing user expectations throughout conversation | Team is diagramming error flows in Visio and documenting responses to identified error categories. Introductory/welcome content was finalized by Megan on 1/27. | Megan to review parameter prompts for authentication by 2/24. | Grace/ Sunayna/ Nicole

## Slide 5: UX Workstream
Item | Description | Status | Next Steps | Owner
User Research | Efforts to elicit design inputs from end user research and testing | Worked with Grace, Sunayna, Julie, and Devs to finalize a rough draft of the user test flow and the content for the DF Prototype for Veterans and a separate test flow for Caregivers. Met with Shane and went over: Test plan's user tasks and scenarios. Content for DF prototype. Moderator guide questions for each task. | Final tweaking of task scenarios, moderator script, and moderator guide questions. Get Julie's final approval on the Test Plan B Mural. Send Test Plan B Mural to Luciana for final feedback/approval. After Luciana's approval, Dev Team can start on the DF prototype for User Test Plan B. Refine User Test Plan B formal document and send document along with access to DF prototype to Shane for final approval. Kick-off meeting with Perigean for Veteran and Caregiver recruiting. | Nina

## Slide 6: Technology Workstream
Item | Description | Status | Next Steps | Owner
Google DialogFlow | Implementing Voicebot solution in DialogFlow | Build out new feature requirements for User test session B Add Unit test coverage | Deploy new environment for User test session B with new phone number | Josh / Nicole
Cloud Webhook Service | Cloud Function being used for webhooks in DialogFlow | Adding new mock data for test users in BAH Google cloud function Design Architecture diagram to submit to VA cloud services team | Request for use of VA's enterprise cloud systems in process Enterprise Cloud Solution Office (ECSO) ticket #ECSOI-419 created, last updated on 2/3 | Nicole / Josh

## Slide 7: Integration Workstream
Item | Description | Status | Next Steps | Owner
Integrating into Cisco IVR Telephony | Identifying how calls with transfer from IVR to Voicebot to IVR | VA is procuring DialogFlow licenses Authentication / Integration call held with Klay and Christian on 1/17 Email sent to Trish Dang, Regina Yount, and Brenda Torress-Hill for authentication methods for Voicebot | Team to sign up for access to WebEx Cisco Cloud Waiting for response from authentication methods Will be asked in meeting with Regina | Booz Allen
VA Sandbox | A sandbox Voicebot development | VA working on creating sandbox | Once sandbox is set-up, Booz Allen will set-up Voicebot and begin exploring integration into VA services | VA

## Slide 8: Ad Hoc Items
Item​ | Description​ | Status​ | Next Steps​ | Owner​
ATO acquisition | DTC preparing for ATO | Booz Allen provided response to questions in PTA on 1/17 Met with DTC on 1/30 to review PTA Booz Allen updated PTA based on additional guidance. | ATO approval estimated to take 7-11 months ISSO to complete review and provide concurrence by 2/9 | Booz Allen / VA
HCD Insights around Claim Status / Claim Status Tool | Identify insights from User Session A which relate to claim status | Insights and respective quotes from User Session A sent on 2/2 Booz Allen re-sent with more details on 2/8 | Kate to review, suggest tweaks where necessary | Julie / Kate
Meeting with Regina | Voicebot to meet with Regina and team to share User Session A insights | Meeting with Regina scheduled for 2/15 at 9am | Booz Allen preparing deck for meeting. Deck will provide insights gathered from Session A, high level overview of coming Session B, and next steps / discussion points | Booz Allen
Project Documentation | Ensuring all project documentation is accessible | Booz Allen working on Project Summary deck | Project Summary deck is being reviewed internally New resource to be used to continue to iterate on deck | Booz Allen

## Slide 9: Open Forum
Questions / Open Discussion

## Slide 10: Appendix

## Slide 11: Project Overview
Detailed scope for Omnichannel project will be voice.
Discovery through building and learning—build it, learn from it, iterate it.
  With an overall strategy of transitioning MyVA411, transition VBA to using a Natural Language Understanding (NLU) platform.
    Determine the problem categories and point of transition.
  Through learning and understanding how self-service and triage can be supported through voice channels, assess another product which may replace AudioCARE.
  Stipulations:
    Projects must have a customer experience and Omnichannel mindset toward best customer experience for Veterans.
    Small iterative releases, solutions to run in parallel with existing solutions to Veterans are not negatively affected by our transitions.
    All products must have Veteran input.